## Sheet1
PGI IN EMERGENCIES
Plan of Arrival Checklist
A Surge Plan of Arrival should be created before arrival in country by the Team Leader in coordination with the Operations Manager. Each task should be assigned to a Surge team member, and this checklist is intended to help the Team Leader track progress.
| Task |  |  | Documentation/Template | PGI supports/undertakes | comments
Pre-departure | Situation Awareness | Secondary data review & mapping |  | Code of conduct | PGI | Extract all data realted to PGI. Use TOOL 2.4 for guiding questions
|  |  |  | Situation reports and other impact information | PGI
|  |  |  | OCHA or other assessment team reports | PGI
|  |  |  | Contingencies and secondary effects | PGI
|  |  |  | Other elevant background documents | PGI
|  | Review NS plans |  | National plan and annual reports | PGI
|  | PGI Needs Analysis (secondary data) |  | Government data, reports from other organisations | PGI
| Coordination | Understand RC/RC Context |  | Agreements in place | PGI | Learn about RCRC PGI work
|  |  |  | Documentation from previous PGI rotations | PGI
|  |  |  | Documentation on ICRC role, if relevant | PGI
|  |  |  | Contact lists for Geneva, region and ICRC | PGI
|  |  |  | Documentation on NS capacity and actions | PGI
| Team Admin & Management | Get familiar with surge procedures |  | Competencies and skills of team members | PGI | Understand your role and responsabilities
|  |  |  | Resources available (equipment, cash) | PGI
|  |  |  | Reporting lines and responsibilities | PGI
|  |  |  | Preliminary tasking | PGI
|  |  |  | Role profile and team TOR (if available) | PGI
Days 1-3 | Situation Awareness | Key Informant Interviews (with volunteers, key stakeholders) |  | PGI Assessment matrix, PGI analysis template | PGI | Interview and meet as many people as possible/gather as many reports as possible
|  | Security Assessment |  | Security pack | Security
|  | Logistics Assessment |  |  | Locistics
|  | Protection and gender assessment reports from other organizations |  | CARE rapid gender assessment, humanitarian response plan | PGI
|  | Transition to recovery and Handover Planning |  | Transition and Handover Plan | PGI
|  | Sectoral Awareness |  | PGI Assessment matrix, PGI analysis template | PGI
|  | Site Visits |  |  | PGI
| Coordination | Establish capacity to communicate | Equipment: radio, phones, satcom, internet | IT/Telecoms evaluation | Admin/IT | Understand humanitarian context and determine capacities
|  |  | Translation as needed |  | Admin/IT
|  | Meet with: | National Society (SG, PGI FP, Volunteer manager, PSS, RFL) | PGI analysis template | PGI
|  |  | IFRC Delegation |  | PGI
|  |  | Host Government (coordination authority, disaster management authority, line ministries) |  | PGI
|  |  | UN Agencies (UNHCR, UNICEF, UNFPA…) and NGOs (CARE, IPPF...) |  | PGI
|  |  | Donors (ECHO/DFID/USAID, etc) |  | PGI
|  | Determine National Society capacity and actions |  | PGI assessment matrix (PGI capacity self-asessment), PGI analysis template | PGI
|  | Identify PNS on-site or in pipeline |  |  | PGI
|  | Establish roles and responsabilities (including with NS) |  |  | PGI
|  | 4W info tracker for RC and external activities |  | 4W Template | PGI/IM
|  | Identify Protection cluster and sub-cluster leads |  |  | PGI
|  | Collect and create maps of affected areas |  |  | PGI
| Team Admin & Management | Notify Geneva of arrival |  |  | PGI | Be aware this is what the team leader is working on
|  | Set up base of operations |  | *Base of operations set up checklist | HEoPs/Admin
|  | Fix personal support | Shelter |  | Admin
|  |  | Food |  | Admin
|  |  | Transport |  | Admin/Fleet
|  | Establish Team Org-Chart |  | Org Chart Template | PMER/IM
|  |  |  | *Common cross sector functions list | PMER/IM
|  | Create contact list |  | Contact list template | Admin
|  | Join operation whatsapp/mailing lists |  |  | PGI
|  | Establish file management and document storage |  | File structure guidance | PGI/IM/PMER
|  | Schedule meetings and assign roles to team members/volunteers |  | Meeting notes template | PGI
|  | Develop standard briefing package for meetings |  | Briefing Agenda, schedule, powerpoint | PGI
| Required Deliverables | Assessment Plan & Schedule |  | Assessment Plan & Schedule Template | PGI | Check assessment plan and ensure PGI assessment needs are included. Add PGI info in reports.
|  | Security, Contingency and Medivac Plans |  | Security Plan Template | PGI
|  | Daily Situation reports | Day 1 | Situation Report Template | PGI
|  |  | Day 2 |  | PGI
|  |  | Day 3 |  | PGI
Days 4-5 | Situation Analysis | Scenario Mapping |  | Scenario Mapping Template | PGI | Contribute to the team analysis report and response options by presenting the PGI findings (secondary data) and suggestions
| Response Analysis & Decision Making | Start identifying and analysing response options |  |  | PGI
|  | Risk Assessment |  | Risk planning matrix | PGI
|  | Cost efficiency/effectiveness |  |  | PGI
|  | Disaster Risk Reduction |  |  | PGI
|  | Feasbility Testing/SWOT |  | SWOT Template | PGI
| Ongoing Assessments | Determine need for further Team movement/field assessment |  | Needs/Capacity Analysis Form, Camp Assessment Template, Assessment Report Template | PGI
| Coordination | Remain in contact with Geneva and local partners |  |  | PGI
| Required Deliverables | Situation Analysis and Response Reccomendations |  |  | PGI | Make sure PGI is included in response reccomendations
|  | 4Ws |  | 4Ws Template | PGI
PGI
Day 6 onwards | Service Delivery Operational Planning | Plan of Action |  | Plan of Action with Logframe | PGI
|  | Request additional supplies and personnel as needed |  |  | PGI
|  | Identify further meeting needs |  |  | PGI
| Ongoing Assessments | Continue assessments, as needed |  | Needs/Capacity Analysis Form, Camp Assessment Template, Assessment Report Template | PGI | Look into feedback, myths and rumours circulating in the communities and share with teams
| Coordination | Remain in contact with Geneva and local partners |  |  | PGI
| Required Deliverables | Plan of Action |  | Plan of Action with Logframe | PGI | EnsurePGI component is included
|  | Budget & Budget Narrative |  | Budget template and guidance | PGI
|  | Funding Scalability Plan |  |  | PGI
|  | Operations Plan |  | Sample Operations Plan | PGI
|  | Monitoring |  |  | PGI
|  | Revised Plan of Action |  | Plan of Action with Logframe | PGI